## Dashboard
VOYEX CRM Project Readiness Tracker
Metric | Formula
Total Tasks | 60
Done | 0
In Progress | 0
Blocked | 0
Readiness % | 0%

## Checklist
Phase | Module | Task | Priority | Status | Owner | Target Date | Notes
Phase 0 - Safety | System | Backup database | High | Not Started
Phase 0 - Safety | Git | Create working branch | High | Not Started
Phase 0 - Safety | Production | Check APP_DEBUG=false | High | Not Started
Phase 0 - Safety | Security | Remove/guard debug routes | High | Not Started
Phase 1 - Audit | Database | Audit migrations | High | Not Started
Phase 1 - Audit | Models | Audit model relationships | High | Not Started
Phase 1 - Audit | Routes | Audit web.php and route names | High | Not Started
Phase 1 - Audit | Controllers | Audit controllers | High | Not Started
Phase 1 - Audit | Views | Audit Blade views | High | Not Started
Phase 1 - Audit | Access | Audit permissions/modules | High | Not Started
Phase 1 - Audit | Workflow | Audit status usage | High | Not Started
Phase 2 - Status | Status | Create legacy-to-new status mapping | High | Not Started
Phase 2 - Status | Status | Create enum/config statuses | High | Not Started
Phase 2 - Status | Database | Convert risky enum columns to string if needed | High | Not Started
Phase 2 - Status | UI | Update badges, filters, dashboard queries | High | Not Started
Phase 3 - Inquiry | Inquiry | Require customer/agent relation | High | Not Started
Phase 3 - Inquiry | Inquiry | Complete source options | Medium | Not Started
Phase 3 - Inquiry | Inquiry | Add/verify follow-up history | High | Not Started
Phase 3 - Inquiry | Inquiry | Add Create Itinerary action | High | Not Started
Phase 3 - Inquiry | Inquiry | Lock final inquiry statuses | High | Not Started
Phase 4 - Itinerary | Itinerary | Ensure inquiry/customer relation | High | Not Started
Phase 4 - Itinerary | Itinerary | Ensure chargeable/include flags | High | Not Started
Phase 4 - Itinerary | Itinerary | Verify duplicate and PDF | Medium | Not Started
Phase 4 - Itinerary | Itinerary | Generate quotation from itinerary | High | Not Started
Phase 4 - Itinerary | Itinerary | Lock converted itinerary | High | Not Started
Phase 5 - Quotation | Quotation | Verify versioning | High | Not Started
Phase 5 - Quotation | Quotation | Snapshot contract rate and markup | High | Not Started
Phase 5 - Quotation | Quotation | Validate total/final amount | High | Not Started
Phase 5 - Quotation | Quotation | Revision flow without overwriting accepted quotation | High | Not Started
Phase 5 - Quotation | Quotation | Lock accepted/converted quotation | High | Not Started
Phase 6 - Validation | Validation | Dedicated validation page | High | Not Started
Phase 6 - Validation | Validation | Item detail modal | High | Not Started
Phase 6 - Validation | Validation | Rate and markup validation | High | Not Started
Phase 6 - Validation | Validation | Block send if invalid | High | Not Started
Phase 6 - Validation | Validation | Validation log | Medium | Not Started
Phase 7 - Booking | Booking | Convert only from accepted quotation | High | Not Started
Phase 7 - Booking | Booking | Store quotation/itinerary reference | High | Not Started
Phase 7 - Booking | Booking | Create booking items/snapshot | High | Not Started
Phase 7 - Booking | Booking | Generate invoice | High | Not Started
Phase 7 - Booking | Booking | Close only after settlement | High | Not Started
Phase 8 - Finance | Invoice | Support DP invoice | High | Not Started
Phase 8 - Finance | Invoice | Support balance invoice | High | Not Started
Phase 8 - Finance | Payment | Partial payment | High | Not Started
Phase 8 - Finance | Payment | Overpayment handling | High | Not Started
Phase 8 - Finance | Payment | Refund/deposit handling | High | Not Started
Phase 9 - Operation | Operation | Vendor confirmation | Medium | Not Started
Phase 9 - Operation | Operation | Driver/guide assignment | Medium | Not Started
Phase 9 - Operation | Operation | SPK generation | Medium | Not Started
Phase 9 - Operation | Operation | Service started/completed | High | Not Started
Phase 9 - Operation | Operation | Issue report | Medium | Not Started
Phase 10 - Settlement | Adjustment | Adjustment approval | High | Not Started
Phase 10 - Settlement | Adjustment | Additional invoice/refund/deposit result | High | Not Started
Phase 10 - Settlement | Settlement | Settlement review page | High | Not Started
Phase 10 - Settlement | Settlement | Close booking only when settled | High | Not Started
Phase 11 - Production | Production | Route test | High | Not Started
Phase 11 - Production | Access | Permission test | High | Not Started
Phase 11 - Production | Frontend | Vite build | High | Not Started
Phase 11 - Production | Storage | Storage link | Medium | Not Started
Phase 11 - Production | Scheduler | Queue/scheduler | Medium | Not Started
Phase 11 - Production | Ops | Backup/log review | High | Not Started

## Status Reference
Module | Recommended Status | Final? | Notes
Inquiry | new_request | No
Inquiry | need_customer_data | No
Inquiry | registered | No
Inquiry | assigned | No
Inquiry | contacted | No
Inquiry | waiting_customer | No
Inquiry | qualified | No
Inquiry | unqualified | Yes
Inquiry | itinerary_in_progress | No
Inquiry | quotation_in_progress | No
Inquiry | quotation_sent | No
Inquiry | under_negotiation | No
Inquiry | accepted | No
Inquiry | converted_to_booking | Yes
Inquiry | lost | Yes
Inquiry | cancelled | Yes
Inquiry | expired | Yes
Itinerary | draft | No
Itinerary | in_review | No
Itinerary | approved | No
Itinerary | quotation_generated | No
Itinerary | revised | No
Itinerary | confirmed | No
Itinerary | converted_to_booking | Yes
Itinerary | cancelled | Yes
Itinerary | archived | No
Quotation | draft | No
Quotation | pending_validation | No
Quotation | validated | No
Quotation | sent | No
Quotation | revision_requested | No
Quotation | revised | No
Quotation | accepted | No
Quotation | rejected | Yes
Quotation | expired | Yes
Quotation | converted | No
Quotation | superseded | No
Quotation | amended | No
Quotation | cancelled | Yes
Validation | pending | No
Validation | valid | No
Validation | invalid | No
Validation | need_update | No
Validation | expired_rate | No
Booking | pending_confirmation | No
Booking | confirmed | No
Booking | awaiting_dp | No
Booking | dp_received | No
Booking | awaiting_balance | No
Booking | ready_to_operate | No
Booking | in_operation | No
Booking | service_completed | No
Booking | completed_unsettled | No
Booking | completed_settled | No
Booking | closed | Yes
Booking | cancelled | Yes
Invoice | draft | No
Invoice | issued | No
Invoice | partially_paid | No
Invoice | paid | Yes
Invoice | overpaid | No
Invoice | revised | No
Invoice | void | Yes
Invoice | cancelled | Yes
Payment | pending | No
Payment | waiting_confirmation | No
Payment | confirmed | No
Payment | rejected | Yes
Payment | refunded | Yes
Payment | allocated_as_deposit | Yes
Adjustment | draft | No
Adjustment | pending_approval | No
Adjustment | approved | No
Adjustment | rejected | Yes
Adjustment | applied | Yes
Adjustment | cancelled | Yes
Settlement | pending_review | No
Settlement | outstanding_balance | No
Settlement | overpaid | No
Settlement | refund_required | No
Settlement | deposit_recorded | No
Settlement | settled | Yes

## Readiness Gate
Gate | Pass Criteria | Status | Notes
Business Flow | Customer → Inquiry → Itinerary → Quotation → Booking works end-to-end | Not Started
Status Integrity | No inconsistent status between DB/model/controller/view | Not Started
Quotation Validation | Quotation cannot be sent before required validation is complete | Not Started
Booking Conversion | Booking only from accepted quotation | Not Started
Finance Integrity | Invoice/payment/balance/overpayment accurate | Not Started
Adjustment | Post-booking changes use adjustment, not direct edit | Not Started
Settlement | Booking closes only after service + finance settled | Not Started
Permission | Roles cannot access unauthorized modules/routes | Not Started
Production | APP_DEBUG=false, Vite build, storage, scheduler, backup ready | Not Started